## Sheet1
Nama Activity | Section | Due Date Plan
Folow up NOR ke customer | de | 2019-07-25
Release DCIL | de | 2019-07-25
Release original drawing | de | 2019-07-25
Release original circuit list | de | 2019-07-25
Release original kakouzu | de | 2019-07-25
Upload EPL di AS400 + Release oracle address | de | 2019-07-25
Release part list matrix | de | 2019-07-25
Release TSQ | de | 2019-07-25
Release nameplate matrik | de | 2019-07-25
Release commonize circuit | de | 2019-07-25
Release commonize tube | de | 2019-07-25
Release PA drawing & matrik | de | 2019-07-25
Approval nameplate | de | 2019-07-25
Release Engineering Drawing | de | 2019-07-25
Release circuit list | de | 2019-07-25
Release form obsolete | de | 2019-07-25
Scrab document obsolete | de | 2019-07-25
Release time study F/A KE PRODUKSI (Housing, Setting, Taping, SP, MSP, Offline) | pp | 2019-07-25
Release drawing (Sakehame, Atohame, Plug) | pp | 2019-07-25
WO input matrik (Housing, SP, MSP, Offline, Central Plug) | pp | 2019-07-25
WO cek matrik (SP, Offline) | pp | 2019-07-25
Cek matrik (housing, Msp, Central Plug) | pp | 2019-07-25
WO REVISI DRAFT SAO | pp | 2019-07-25
WO REPAIR SAO | pp | 2019-07-25
RELEASE WASURENBO | pp | 2019-07-25
WO ANALISA SIZE BOX | pp | 2019-07-25
WO ID BOX MATERIAL | pp | 2019-07-25
REPLACE ID & BOX MATERIAL | pp | 2019-07-25
RELEASE ADRESSING CCT | pp | 2019-07-25
REPLACE & TEMPEL ID CCT | pp | 2019-07-25
REPLACE & TEMPEL ID SAO SUB ASSY | pp | 2019-07-25
RELEASE MATRIKS VARIAN BONDER | pp | 2019-07-25
UPDATE NO MATERIAL JIG DWG | pp | 2019-07-25
UPDATE NO PROGRAM DI SP | pp | 2019-07-25
UPDATE NO PROGRAM DI OFFLINE | pp | 2019-07-25
Release dan Sosialisasi Henkaten | pp | 2019-07-25
WO ENG. PACKET/ ENG. ORI JAPAN | pp | 2019-07-25
Supply W/H buzzer ke produksi | qmp | 2019-07-25
Trial program EC-1,2 + AB | qmp | 2019-07-25
Validasi program area Inspeksi | qmp | 2019-07-25
Trial program SP1+SP2+AB | qmp | 2019-07-25
Cek New Part Equipment | qmp | 2019-07-25
Check dimensi / jig drawing | qmp | 2019-07-25
Update revision record all JB | qmp | 2019-07-25
Up date JB Justment | qmp | 2019-07-25
Validasi mesin fuse | qmp | 2019-07-25
IPI check/TR check | qmp | 2019-07-25
Release Symbol Nameplate (untuk approval NP) | qmp | 2019-07-25
Pengembalian form dan dokumen obsolete | qmp | 2019-07-25
Trial program SP1+SP2 | qmp | 2019-07-25
WO Ori drawing ke DE | qp | 2019-07-25
Compare drawaing | qp | 2019-07-25
Trial metode baru area inspeksi | qp | 2019-07-25
Change SWCT/Time Study | qp | 2019-07-25
Revisi matrik inspection area (MSP / Fuse EC/ Dim Check / Siage/ Visual / Double check) | qp | 2019-07-25
Revisi Important point / inspection point | qp | 2019-07-25
Update visual matting | qp | 2019-07-25
Update harness sample | qp | 2019-07-25
Update sample wire / terminal PA | qp | 2019-07-25
WO input matrik inspection area ke FAE | qp | 2019-07-25
WO input patern fuse ke FAE | qp | 2019-07-25
WO analisa size box ke NYS | qp | 2019-07-25
WO ID dan box Material ke NYS | qp | 2019-07-25
WO cek matrik ke QMP | qp | 2019-07-25
WO validasi hasil input patern fuse ke QMP | qp | 2019-07-25
Sosialisasi henkaten | qp | 2019-07-25
Release henkaten | qp | 2019-07-25
Release SWCT /Time Study | qp | 2019-07-25
Replace ID material pada box / ID dikasihkan ke WHS | qp | 2019-07-25
(fa) check stock part / order part | engineering | 2019-07-25
(fa) check new equipment / order new equipment | engineering | 2019-07-25
(fa) repair box sakihame / repair meja insert plug | engineering | 2019-07-25
(fa) repair housing / mapping duct | engineering | 2019-07-25
(fa) repair navigasi | engineering | 2019-07-25
(fa) repair meja MSU | engineering | 2019-07-25
(fa) input matrik (Housing, Msp, Plug, SP, Offline, DIM/VIS) | engineering | 2019-07-25
(fa) share henkaten jig | engineering | 2019-07-25
(fa) repair jig drawing / repair jig ( SP/JIG/OFFLINE) | engineering | 2019-07-25
(fa) Release draft SAO ke PP | engineering | 2019-07-25
(fa) repair ID papan sao/add papan sao | engineering | 2019-07-25
(fa) kirim data matrik separator ke NYS | engineering | 2019-07-25
(fa) Repair/penambahan no material | engineering | 2019-07-25
(fa) repair ec/chg cf/add cf | engineering | 2019-07-25
(fa) input/chg program ec , chg ec dwg | engineering | 2019-07-25
(fa) add program CB EC/DIM/VIS | prod | 2019-07-25
(fa) Implementasi D/C & cek item perubahan | prod | 2019-07-25
(fa) karantina old part + cct | prod | 2019-07-25
(fa) Pengembalian material | prod | 2019-07-25
(fa) scrab old part dan circuit | prod | 2019-07-25
(fa) trial metode baru bersama QC & PP | prod | 2019-07-25
(fa) Supply material | prod | 2019-07-25
(fa) cutting tube | prod | 2019-07-25
(fa) check stock cct/material | prod | 2019-07-25
(fa) buat stock SP1 + A/B | prod | 2019-07-25
(fa) buat stock sub assy | prod | 2019-07-25
(fa) Repair WH buzzer | prod | 2019-07-25
(fa) Ganti N/P pada W/H buzzer | prod | 2019-07-25
(fa) Kirim hasil tial analisa material tube ke NYS | prod | 2019-07-25
(fa) Pengembalian box material ke NYS | prod | 2019-07-25
(fa) Pengembalian ID sample N/P BO ke NYS | prod | 2019-07-25
(fa) Pengembalian withdrawal | prod | 2019-07-25
(fa) Pengembalian form dan dokumen obsolete | prod | 2019-07-25
(fa) Mengosongkan wip housing | prod | 2019-07-25
(fa) Mengosongkan wip Setting | prod | 2019-07-25
(fa) Mengosongkan wip Taping | prod | 2019-07-25
(fa) Mengosongkan wip inspeksi | prod | 2019-07-25
(fa) Karantina dan pengembalian sisa label | prod | 2019-07-25
(fa) Karantina dan pengembalian sisa np | prod | 2019-07-25
(fa) Karantina dan pengembalian sisa cik | prod | 2019-07-25
(pa) cutting circuit | prod | 2019-07-25
(pa) Supply circuit | prod | 2019-07-25
(pa) Pengembalian box material ke NYS | prod | 2019-07-25
(pa) Pengembalian kanban cutting | prod | 2019-07-25
(pa) Pengembalian kanban drawing | prod | 2019-07-25
(pa) Release machine loading shield | nys | 2019-07-25
(pa) Release machine loading cct | nys | 2019-07-25
(pa) Release machine loading AB | nys | 2019-07-25
(pa) Release machine loading tube | nys | 2019-07-25
(pa) Replace/release kanban cct | nys | 2019-07-25
(pa) Replace/release kanban material PA | nys | 2019-07-25
(pa) WO kode RFID kanban | nys | 2019-07-25
(pa) Update database e-kanban | nys | 2019-07-25
(pa) Update patch bonder | nys | 2019-07-25
(pa) Release list cct delete | nys | 2019-07-25
(fa) Kirim analisa size box ke WHS / CTB | nys | 2019-07-25
(fa) Release analisa type box ke PP dan QP,QMP | nys | 2019-07-25
(fa) Release box material ke PP dan QP,QMP | nys | 2019-07-25
(fa) Release ID material ke PP dan QP, QMP | nys | 2019-07-25
(fa) Change identitas part store | nys | 2019-07-25
(fa) Release / Replace CIK | nys | 2019-07-25
(fa) Release kanban WU / BT | nys | 2019-07-25
(fa) Replace / Release ID Sample Nameplate FA / PA | nys | 2019-07-25
(pp pa) Release dan sosialisai henkaten | nys | 2019-07-25
(pp pa) WO input matrik | nys | 2019-07-25
(pp pa) WO bonding std | nys | 2019-07-25
(pp pa) Release addresing cct | nys | 2019-07-25
(pp pa) Replace dan tempel id sao | nys | 2019-07-25
(pp pa) Cek matrik | nys | 2019-07-25
(pp pa) WO equipment | nys | 2019-07-25
(pp pa) Release mapping flow PA dwg | nys | 2019-07-25
(pp pa) Release matrik maooing flow | nys | 2019-07-25
(pp pa) Addresing acc | nys | 2019-07-25
(pp pa) WO input matrik | nys | 2019-07-25
(pp pa) WO box | nys | 2019-07-25
Check status old part | ic | 2019-07-25
Claimkan dead stock ke customer | ic | 2019-07-25
Release schedule stop order old part | ic | 2019-07-25
Check status new part | ic | 2019-07-25
Order new part, request ETA SAI : | ic | 2019-07-25
Material free SoC | ic | 2019-07-25
List Material CSS | ic | 2019-07-25
Informasi usage per day to WHS | ic | 2019-07-25
Check actual stock old part yang mengalami D/C | whs | 2019-07-25
Identifikasi new part | whs | 2019-07-25
Supply new part | whs | 2019-07-25
Replace ID Material (R/C) | whs | 2019-07-25
Kirim hasil analisa size box ke NYS | whs | 2019-07-25
Supply material common ke line : ……………… | whs | 2019-07-25
Request SO ke PLB | whs | 2019-07-25
(pa) check applikator | engineering | 2019-07-25
(pa) pembuatan crimping standart dan bonder standart | engineering | 2019-07-25
(pa) setting machine loading | engineering | 2019-07-25
(pa) Pengembalian form dan dokumen obsolete | engineering | 2019-07-25
(pa) Input kode RFID ke Karakuri | engineering | 2019-07-25
(pa) Release mapping applikator | engineering | 2019-07-25
(pa) order new equipment, request ETA SAI : | engineering | 2019-07-25
Isi no box/ polytainer pada kartu imp dc | exim | 2019-07-25
Release Harness Price | fa | 2019-07-25
Release UMH | fa | 2019-07-25
Request Price dan UMH ke FA | ppc | 2019-07-25
Update assy code di assy plan | ppc | 2019-07-25
Update suffix level di heikinka, assy plan, dan SPP | ppc | 2019-07-25
Update component packing di oracle | ppc | 2019-07-25
Release analisa S/R max loading per shift | ppc | 2019-07-25
Release Countdown assy | ppc | 2019-07-25
(nameplate) Print sample label | ppc | 2019-07-25
(nameplate) Pembuatan approval nameplate | ppc | 2019-07-25
(nameplate) Print sample name plate to DE+QA+kantong name plate | ppc | 2019-07-25
(nameplate) Print name plate baru | ppc | 2019-07-25
(nameplate) Scrap name plate | ppc | 2019-07-25
(D/C) Distribusi DCIL | ppc | 2019-07-25
(D/C) Request NOR official ke Cust | ppc | 2019-07-25
(D/C) Prepare NOR, checksheet dan kartu implementasi DC | ppc | 2019-07-25
(D/C) Check list implementasi | ppc | 2019-07-25
(D/C) Release form obsolete (COPY NOR) | ppc | 2019-07-25
(D/C) Scrab (COPY NOR) | ppc | 2019-07-25
(D/C) Kirim GJN ke customer | ppc | 2019-07-25
(D/C) Konfirmasi ke Cust. Plan SAI implementasi NOR (jika tidak sesuai requirement Cust.) - Format GJN | ppc | 2019-07-25
(D/C) Supply heikinka, nameplate, CIK dan Label | ppc | 2019-07-25
(D/C) Update D/C Matrik | ppc | 2019-07-25
Nb :
1. Data yang akan terisi ke database adalah activity yang Due Date Plan nya terisi. Jika Due Date Plan nya tidak terisi, maka activity tidak akan masuk ke database